## PROJECT PROFILE
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | PRJ_Registration001
Project Name | Registration
Prepared/Modified by | Role | Date of Preparation
Arun | Tester | 2016-01-04
Reviewed by | Role | Date of Review
Latha | SME
Approved by | Role | Date of Approval
Gaurav | Test Manager
Circulation List
Version Number | 1

## DEFECT TRACKING SHEET
Project ID: PRJ_Registration001 |  | Project Name : Registration
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_LOGIN_001 | AUTHORITY LOGIN | The User name field in the page is found to accept characters less than 4 | Detailed Description: The User name field in the page is found to accept characters less than 4 Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Authority login 4. Enter Invalid Username(less than 4 characters) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the any data in the Username field. The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_UserName_02 | [5 empty] | drg
DF_LOGIN_002 | AUTHORITY LOGIN | The User name field in the page is found to accept characters more than 8 | Detailed Description: The User name field in the page is found to accept characters more than 8 Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Authority login 4. Enter Invalid Username(more than 8 characters) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the any data in the Username field. The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_UserName_03
DF_LOGIN_003 | AUTHORITY LOGIN | The password field in the page is found to accept characters less than 3 | Detailed Description: The password field in the page is found to accept characters less than 3 Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Authority login 4. Enter Invalid password(less than 3 characters) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the any data in the password field. The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_Pwd_02
DF_LOGIN_004 | AUTHORITY LOGIN | The password field in the page is found to accept characters more than 8 | Detailed Description: The password field in the page is found to accept characters more than 8 Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Authority login 4. Enter Invalid password(more than 8 characters) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the any data in the password field. The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2016-12-11 | Aman |  |  | Test Cycle 1 | TC_Pwd_03
DF_LOGIN_005 | FLIGHT BASED ON PERIOD | The From date field in the flight details page is found older than current date. | Detailed Description: The From date field in the flight details page is found older than current date also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid From date 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the older date in the From field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | high | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_From_02 | [5 empty] | drg
DF_LOGIN_006 | FLIGHT BASED ON PERIOD | The To date field in the flight details page is found older than From date. | Detailed Description: The To date field in the flight details page is found older than From date also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid From date 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the older date in the To field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_To_02 | [5 empty] | drg
DF_LOGIN_007 | FLIGHT BASED ON PLACE | The source field in the flight details is found to accept same place as given in destination | Detailed Description: The source field in the flight details is found to accept same place as given in destination also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid source 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the invalid source.The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_Source_02 | [5 empty] | drg
DF_LOGIN_008 | FLIGHT BASED ON PLACE | The destinatoin field in the flight details is found to accept same place as given in source | Detailed Description: The destination field in the flight details is found to accept same place as given in source also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid source 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the invalid destinatoin.The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_Destination_02 | [5 empty] | drg
DF_LOGIN_009 | FLIGHT BOOKING | The user name field in the flight details page is found to accepts invalid name. | Detailed Description: The user name field in the flight details page is found to accepts invalid name also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid name 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the invalid name.The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_NoPersons_02 | [5 empty] | drg
DF_LOGIN_010 | FLIGHT BOOKING | The email field in the flight details page is found to accepts invalid email. | Detailed Description: The email field in the flight details page is found to accepts invalid email also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid email 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the invalid email.The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_EmailID_02 | [5 empty] | drg
DF_LOGIN_011 | PAYMENT | The card details field is found to accept invalid alpha numerics values | Detailed Description: The card details field is found to accept invalid alpha numerics values also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid card details 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the invalid card details.The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_card_02 | [5 empty] | drg
DF_LOGIN_012 | PAYMENT | The card details field is found to accept more than 10 numbers | Detailed Description: The card details field is found to accept more than 10 numbers also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid card details 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts more than 10 numbers in card details field.The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_card_03 | [5 empty] | drg
|  |  |  | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | [6 empty] | drg
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.